## Scope
# | Work Package | Est. Effort (pds) | In Charge | Deadline | Status | Actual Effort (pds) | Notes
1 | Stage 1: Project Initiating (week 1)
1.1 | Report 1 (Project Introduction) | 8 | Bach | Week1 | Done | 8
2 | Stage 2: Project Planning & Initial Requirements (weeks 2-3)
2.1 | Report 3: SRS v0.9 (Overall Requirement) | 12 | Bach | Week2 | Done | 16
2.2 | Vertical Prototypes (Code Demo) | 12 | Dang, Hiep | Week3 | Done | 10
2.3 | Report 2: Project Management Plan v1.0 | 8 | Bach | Week3 | Done | 5
3 | Stage 3: Software Design (weeks 4-5)
3.1 | Vertical Prototypes (POC, or Proof Of Concepts) | 12 | Dang,Nha | Week4 | Done | 10
3.2 | Report 4: SDS v1.0 (High Level Design Specifications) | 14 | Dang | Week4 | Done | 18
3.3 | Report 5: Test Planning (ref Report5_Test Documentation) | 6 | Bach | Week5 | Done | 5
3.4 | Report 3: SRS v1.0 (Detailed Requirements for Iteration 1) | 8 | Bach | Week5 | Done | 10
4 | Stage 4: Implementation (weeks 6-11)
4.1 | Implementation Iteration 1 (weeks 6-7)
4.1.1 | Report 4: Detailed Design Specifications (SDS) v1.1 | 5 | Dang | Week6 | Processing
4.1.2 | Code Package & Unit Testing Report | 58 | Cả nhóm | Week6 | Processing
4. 1.3 | Report 5: Integration Test Cases | 4 | Nha | Week6 | Pending
4. 1.4 | Report 5: Integration Test Report | 4 | Nha | Week7 | Pending
4.1.5 | Report 3: SRS v1.1 (Detailed Requirements for Iteration 2) | 4 | Bach | Week7 | Pending
4.1.6 | Software Package Version 1 | 7 | Dang | Week7 | Pending
4.2 | Implementation Iteration 2 (weeks 8-9)
4.2.1 | Report 4: Detailed Design Specifications (SDS) v1.2 | 5 | Dang | Week8 | Pending
4.2.2 | Code Package & Unit Testing Report | 69 | Dang,Nha,Minh,Hiep | Week8 | Pending
4. 2.3 | Report 5: Integration Test Cases | 5 | Nha | Week8 | Pending
4. 2.4 | Report 5: Integration Test Report | 5 | Nha | Week9 | Pending
4.2.5 | Report 3: SRS v1.2 (Detailed Requirements for Iteration 3) | 4 | Bach | Week9 | Pending
4.2.6 | Software Package Version 2 | 7 | Dang | Week9 | Pending
4.3 | Implementation Iteration 3 (weeks 10-11)
4.3.1 | Report 4: Detailed Design Specifications (SDS) v1.3 | 5 | Dang | Week10 | Pending
4.3.2 | Code Package & Unit Testing Report | 50 | Dang,Nha,Minh,Hiep | Week10 | Pending
4.3.3 | Report 5: Integration Test Cases | 4 | Nha | Week10 | Pending
4.3.4 | Report 5: Integration Test Report | 4 | Nha | Week11 | Pending
4.3.5 | Report 5: System Test Cases | 5 | Nha | Week11 | Pending
4.3.6 | Software Package Version 3 | 5 | Dang | Week11 | Pending
5 | Stage 5: Verification & Validation (weeks 12-13)
5.1 | Report 5: System Test Report | 12 | Nha | Week12 | Pending
5.2 | Report 6: User Guides (Installation Guides, User Manuals) | 10 | Cả nhóm | Week12 | Pending
5.3 | Acceptance Test and Support | 10 | Nha | Week13 | Pending
5.4 | Final Software Package (Documents, Source Codes, etc.) | 4 | Cả nhóm | Week13 | Pending
6 | Stage 6: Closing (week 14)
6.1 | Report 7: Final Project Report | 8 | Cả nhóm | Week14 | Pending
6.2 | Presentation File | 1 | Cả nhóm | Week14 | Pending
| Total | 375

## Change Request
ID | Chức năng/Màn hình | Nội dung thay đổi | Actor | Loại thay đổi | Phạm vi ảnh hưởng | Tính khả thi | Trạng thái | Nguồn YC | Note
1 | Giáo viên tạo một lớp(CRUD) |  | Teacher | Thêm mới chức năng | rp1, rp2, rp3, rp4, code | có thể code |  | Hội đồng
2 | Giáo viên thêm học sinh vào lớp theo gmail |  | Teacher | Thêm mới chức năng | rp1, rp2, rp3, rp4, code | có thể code |  | Hội đồng
3 | Học sinh xem tài nguyên của lớp |  | Teacher | Thêm mới chức năng | rp1, rp2, rp3, rp4, code | có thể code |  | Hội đồng
4 | Giáo viên tạo/sửa/xoá tài nguyên/bài tập giảng dạy lên hub của lớp | Giáo viên có thể đẩy tài nguyên của lớp như: bài giảng, tài liệu tham khảo hoặc giao bài tập cho lớp thực hiện | Teacher | Thêm mới chức năng | rp1, rp2, rp3, rp4, code | có thể code |  | Hội đồng
5 | Giáo viên tạo/sửa/xoá bài tập lên hub của lớp |  | Teacher | Thêm mới chức năng | rp1, rp2, rp3, rp4, code | có thể code |  | Hội đồng
6 | Giáo viên giao bài (assigned) deadline cho học sinh trong lớp |  | Teacher | Thêm mới chức năng | rp1, rp2, rp3, rp4, code | có thể code |  | Hội đồng
7 | Học sinh xem tài nguyên giảng dạy của lớp |  | Pupil | Thêm mới chức năng | rp1, rp2, rp3, rp4, code | có thể code |  | Hội đồng
8 | Học sinh nộp bài tập (điền text/upload file) để hoàn thiện bài tập được giáo viên giao |  | Pupil | Thêm mới chức năng | rp1, rp2, rp3, rp4, code | có thể code |  | Hội đồng
9 | Giáo viên xem bài tập học sinh đã nộp |  | Teacher | Thêm mới chức năng | rp1, rp2, rp3, rp4, code | có thể code |  | Hội đồng
10 | giáo viên gửi giáo án cho trưởng môn duyệt |  | Teacher | Thêm mới chức năng | rp1, rp2, rp3, rp4, code | có thể code |  | Hội đồng
11 | Trưởng môn duyệt giáo án của giáo viên | Trưởng bộ xem và duyệt giáo áo của giáo viên | Mod (trưởng môn) | Thêm mới chức năng | rp1, rp2, rp3, rp4, code | có thể code |  | Hội đồng | Giáo viên upload tài liệu để tạo giáo án cần được mod phê duyệt trước khi sử dụng
12 | thêm role IT management để quản lý các system prompt thay vì hiệu trưởng |  | IT management | Thay đổi chức năng | rp1, rp2, rp3, rp4, code | có thể code |  | Hội đồng | hiệu trưởng không biết về tech nên phải tách role
13 | Xem thống kê (số bài giảng đc tạo bởi AI, số slide được tạo bởi AI) của bài giảng được tạo bởi giáo viên |  | Admin | Thay đổi chức năng | rp1, rp2, rp3, rp4, code | có thể code |  | Hội đồng
Để ý một số vấn đề:
Phân tích kỹ requirement cho các tính năng bổ sung
1. Lớp học kết thúc, học sinh lên lớp trên thì tài nguyên lớp học đó đối với GV, đối với HS sẽ như thế nào ?
2. Tính năng báo cáo: đánh giá xem hiệu trưởng cần báo cáo nào ?
3. Bổ sung main workflow cho tính năng bổ sung
4. Sắp xếp các yc này vào iter => lập lại plan
bổ sung tiền xử lý dữ liệu vào rp 3

## WBS
Function/Screen | Type | Feature | Sub Feature | Function/Screen Description | Level* | Est. Effort | Planned | Status | Notes
Login / Logout (Google SSO) | Non-UI | Common | Login & Logout (SSO) | User login and logout via Google Single Sign-On; registration and authentication are handled by Google | Simple | 5 | Iteration 2 | Coded | UC-02, UC-03 - Coded: Google ID token/JWT authentication and refresh-cookie logout
Update Profile Information | Screen | Common | Profile Management | User profile viewing and updating personal information | Simple | 6 | Iteration 2 | Coded | UC-04 - Coded: view/update full name, avatar and contact information
Role-based Access Control (Teacher / Mod / Admin) | Screen | Common | Access Control | Role-based access control for Teacher, Moderator, and Admin roles | Medium | 10 | Iteration 2 | Partially Coded | Partially coded: backend roles and protected Admin/Moderator APIs; frontend route coverage remains incomplete
View Landing Page | Screen | Common | Landing Page | Public homepage for guests/visitors to learn about the platform, its features and teaching tools before register/login | Simple | 5 | Iteration 1 | Coded | UC-01
Create Lesson Plan (AI: from SGK database or uploaded file) | Screen | Lesson | Lesson Plan Creation | AI generates lesson plans from SGK database with lesson/grade/track selection and knowledge filtering | Complex | 41 | Iteration 1 | Coded | UC-24 (merged: AI-from-database + upload-file variants)
Edit Lesson Plan | Screen | Lesson | Lesson Plan Editing | Edit and approve AI-generated lesson plans with runtime modifications | Medium | 14 | Iteration 1 | Coded | UC-28
Export Lesson Plan (PDF / Word) | Screen | Lesson | Lesson Plan Export | Teacher exports a lesson plan to a downloadable file (PDF/Word) for offline use or printing | Simple | 6 | Iteration 2 | Pending | UC-33
Create Slide Outline (AI - no 3d) | Screen | Slide | Slide Outline | Teacher creates a structured slide outline; AI suggests structure before full slide deck generation | Medium | 10 | Iteration 1 | Tested | UC-25
Edit Slide Outline | Screen | Slide | Slide Outline | Teacher reviews and edits AI-generated slide outline before proceeding to full slide deck generation | Simple | 4 | Iteration 1 | Coded | UC-29
Create Slide Deck (AI from Outline) | Screen | Slide | Slide Generation | AI generates slides from approved lesson plans with auto-embedded assets | Complex | 22 | Iteration 1 | Coded | UC-26
Edit Slide Deck | Screen | Slide | Slide Editing | Manual slide editing: text, add/remove/replace assets, upload new assets | Medium | 13 | Iteration 1 | Coded | UC-30
Present Slide Deck (online) | Screen | Slide | Presentation | Online presentation mode with navigation | Medium | 12 | Iteration 2 | Planned | UC-32
Click-to-simulate during Presentation | Screen | Slide | Presentation | Click-to-simulate interactive elements during live presentation | Complex | 14 | Iteration 2 | Pending | No UC — part of presentation UX
Export Slide (HTML for offline use) | Screen | Slide | Slide Export | Teacher exports a slide deck to a downloadable HTML file for offline use | Medium | 8 | Iteration 2 | Pending | UC-34
View 3D Atomic / Molecule Models | Screen | Simulation | Molecular Models | Render interactive 2D and 3D ball-and-stick molecular models for Chemistry | Complex | 20 | Iteration 2 | Partially Coded | UC-58, UC-59 - Partially coded: interactive 3D ball-and-stick and space-filling molecule viewer with AI structure generation; 2D rendering and lesson/slide embedding are not implemented
View Periodic Table | Screen | Simulation | Periodic Table | Interactive periodic table of 118 elements with category colour-coding and phase data; element detail cards; embeddable into lessons/slides (tools & practice page out of scope) | Medium | 12 | Iteration 2 | Partially Coded | UC-57 - Partially coded: 118-element table, filters, detail cards and 3D atom; embedding into lessons/slides is not implemented
Physics Hub (view, detail, customize via AI) | Screen | Simulation | Physics Simulation | Physics phenomena hub with AI chat customization, save to library | Complex | 16 | Iteration 2 | Partially Coded | UC-53, UC-54, UC-55 - Interactive physics hub and detail simulations exist; AI customization is mock-only and customized simulations are not persisted to Personal Library
Simulation & Asset Library Management | Screen | Simulation | Simulation Library | Shared simulation and asset library for embedding across lessons | Medium | 10 | Iteration 2 | Pending | No UC — shared asset/sim infrastructure
Create Test | Screen | Test | Exam Creation | Create exams in 3 formats: 15-minute, 45-minute, and mid-term test | Complex | 18 | Iteration 1 | Pending | UC-27
Edit Test | Screen | Test | Exam Editing | Teacher opens an existing test and edits its questions, answers, or scoring | Medium | 8 | Iteration 1 | Pending | UC-31
Export Test / Exam (Word / PDF) | Screen | Test | Exam Export | Export exams to a downloadable file (Word/PDF) | Simple | 7 | Iteration 2 | Pending | UC-35
View Personal Library (view, open, search own content) | Screen | Personal Library | Library Management | Save and organize lessons, slides, and custom simulations | Medium | 12 | Iteration 2 | Coded | UC-21, UC-22, UC-36, UC-37 - Coded: authenticated per-user library supports list, search, open, rename/update, and delete; lesson plans and molecule simulations are saved from their editors
Submit / Unsubmit Hub Content for Review | Screen | Community Hub | Content Publishing | Publish and share content to Community Hub with visibility levels | Medium | 12 | Iteration 3 | Pending | UC-23
View Community Hub | Screen | Community Hub | Content Discovery | Search and reference Hub content with filters, save to personal library | Medium | 14 | Iteration 3 | Pending | UC-44
View Public Hub Content Detail (Guest preview) | Screen | Community Hub | Content Discovery | Guest user browses and previews published Hub content without an account | Simple | 4 | Iteration 3 | Pending | UC-45
Customize Hub Content | Screen | Community Hub | Content Discovery | Teacher selects a Community Hub content template and saves it to personal hub for customization | Simple | 5 | Iteration 3 | Pending | UC-46
View & Create Content Comments | Screen | Community Hub | Community Feedback | Comment and provide feedback on Hub content | Simple | 8 | Iteration 3 | Pending | UC-47, UC-41 (view Hub comments + create blog comment)
Update / Delete Own Comment | Screen | Community Hub | Community Feedback | User deletes or edits their own comments on Hub content and on blog posts | Simple | 5 | Iteration 3 | Pending | UC-48, UC-49, UC-42, UC-43 (update/delete own comment: Hub + Blog)
Delete Comment on Own Content | Screen | Community Hub | Community Feedback | Teacher removes any comment posted on their own published Hub content | Simple | 4 | Iteration 3 | Pending | UC-50
Report Violating Content | Screen | Community Hub | Content Moderation | Report violating content for moderator review | Simple | 6 | Iteration 3 | Pending | No UC — content reporting
Moderator Account Management | Screen | User & Content Management | Account Management | Moderator account administration: create, temp password, force login change, lock | Medium | 10 | Iteration 3 | Pending | UC-60, UC-61, UC-62 (view, add, delete moderator)
Teacher Account Management | Screen | User & Content Management | Account Management | Teacher account management: view, update status, support, ban | Medium | 12 | Iteration 3 | Pending | UC-13, UC-14, UC-15 (view, add, delete teacher)
Create Notifications (send to subject teachers) | Screen | User & Content Management | Notifications | Send system notifications and emails triggered by events | Medium | 11 | Iteration 3 | Pending | UC-20
View & Manage My Notifications | Screen | User & Content Management | Notifications | View and manage notifications: inbox, mark read, filter, settings | Simple | 6 | Iteration 3 | Pending | UC-05, UC-19 (view my notifications)
View & Filter Activity Log | Screen | User & Content Management | Audit Log | Activity log auto-recording sensitive actions for Mod/Admin review | Simple | 8 | Iteration 3 | Pending | UC-10
Moderate Hub Content (review, approve, reject) | Screen | User & Content Management | Hub Moderation | Moderate Hub content: approve, reject, handle reports, remove | Medium | 11 | Iteration 3 | Pending | UC-06, UC-07, UC-08, UC-09 (list, detail, approve, reject)
Manage Hub (categorize, tag, organize, pin) | Screen | User & Content Management | Hub Management | Manage Hub structure: categorize, tag, organize, pin content | Medium | 7 | Iteration 3 | Pending | No UC — Hub structure management
View / Update AI System Prompts | Screen | User & Content Management | System Configuration | Admin views and updates AI system prompt templates used by LLM for content generation (lesson plans, tests, slides, etc.) | Medium | 10 | Iteration 3 | Pending | UC-11, UC-12 (view + update AI prompts)
View Blog List (reader + moderation) | Screen | Blog | Blog Reading | Teacher, guest, or moderator views the list of community blog posts; moderators see posts matching their assigned subject (role-based access) | Simple | 6 | Iteration 3 | Pending | UC-51, UC-16 (view blog list: reader + moderation)
View Blog Post Detail (reader + moderation) | Screen | Blog | Blog Reading | Teacher, guest, or moderator opens a blog post to read full content and comments; role-based access for moderation | Simple | 7 | Iteration 2 | Partially Coded | UC-52, UC-17 - Partially coded: authenticated reader and moderator detail views; guest preview is not implemented
Edit Own Blog Post | Screen | Blog | Blog Authoring | Teacher edits a blog post they authored to update or correct its content | Medium | 7 | Iteration 2 | Partially Coded | UC-39 - Partially coded: backend PATCH API exists; frontend edit-post UI is not implemented
Remove / Delete Blog Post | Screen | Blog | Blog Moderation | Moderator removes a blog post in their assigned subject (with reason); author deletes their own blog post | Simple | 5 | Iteration 3 | Pending | UC-18, UC-40 (remove blog post: moderator + author)
(*) You can rate the functions' complexity level based on the number of fields on the screens or the number of transactions in the function, with the details as below
Simple | <=7 fields | <=3 transactions
Medium | <=15 fields | <= 7 transactions
Complex | >15 fields | > 7 transactions
In which: | [6 empty] | Planned | Functions | Total Effort
fields: screen components or database table fields | [6 empty] | Iteration 1 | 9 | 135
transactions can be counted actioning UI components, user or database access transactions | [6 empty] | Iteration 2 | 15 | 152
[7 empty] | Iteration 3 | 18 | 144
[7 empty] | Grand Total | 42 | 431
Note on G1: ====== ID#AAAB9lCdUnk kiennt (2026-06-07 07:38:03) Estimated for Coding & Unit-Testing Effort, in man-days

## Q&A
Project Q&As
Date | Question | By | To | Priority | Due Date | Status | Notes (answers or any other notes)
20/05/2026 | Trường mình dùng bộ sách hóa nào? Sắp tới có thay đổi không? | Phỏng vấn GV Hóa |  | Low |  | Closed | Trường (Lê Quý Đôn) hiện chọn bộ Cánh Diều. Từ năm sau sẽ dùng chung một bộ (Kết nối tri thức). Trước đây các trường tự chọn: Kết nối tri thức / Cánh Diều / Chân trời sáng tạo. Các bộ chỉ khác nhau về trình tự chương và nội dung trước/sau, còn kiến thức cơ bản vẫn giống nhau.
20/05/2026 | Sách mới (chương trình cải cách) khác sách cũ thế nào? | Phỏng vấn GV Hóa |  | Medium |  | Closed | Sách mới sát thực tế hơn, đưa nhiều thí nghiệm và kiến thức ứng dụng vào. Câu hỏi không còn hàn lâm/giải toán hóa khó như xưa mà gắn với thực tế (VD: cháy nổ, tính nhiệt tỏa/thu, lượng than cần để đốt cháy). Bài toán hóa dễ hơn nhưng HS phải vận dụng kiến thức liên môn (Toán, Lý, Hóa, Sinh) và phải quan sát, làm thí nghiệm mới trả lời được. GV cũng buộc phải thay đổi, tìm hiểu các bài tập ứng dụng cao.
20/05/2026 | Cấu trúc đề thi hóa hiện nay như thế nào? | Phỏng vấn GV Hóa |  | Medium |  | Closed | Đề thi ĐH hiện chia 3 phần: (1) Trắc nghiệm 18 câu; (2) Trả lời đúng/sai; (3) Trả lời ngắn – tự điền đáp án (không mò được). Phải hiểu bản chất mới làm được phần 2 và 3. Không còn các dạng bài khó kiểu cũ (bài về pH, HNO3 tạo sản phẩm khử NO2/NO/NH4NO3...). HS giỏi Toán thường làm tốt bài tập hóa. Lớp 12 tất cả môn (trừ Văn) đã trắc nghiệm; sắp tới có thể thi trên máy.
20/05/2026 | Khó khăn lớn nhất khi cho HS làm thí nghiệm tại trường? | Phỏng vấn GV Hóa |  | High |  | Closed | Thí nghiệm với hóa chất dễ vẫn làm được, nhưng hóa chất độc hại (clo, phenol, brom...) thì không làm được vì trường KHÔNG có tủ hốt. Phòng thí nghiệm chưa có hệ thống đường nước. Lớp đông (46–48 HS) khó quản lý, chỉ một đèn cồn đổ là nguy hiểm. Vì vậy GV thường làm thí nghiệm biểu diễn ngay trên lớp hoặc chiếu video thí nghiệm đã quay sẵn.
20/05/2026 | Thí nghiệm thật vs video: ưu/nhược điểm? Nguồn video lấy ở đâu? | Phỏng vấn GV Hóa |  | Medium |  | Closed | Thí nghiệm thật có thể thành công hoặc không; video luôn thành công, kết quả chuẩn, tiết kiệm thời gian – nhưng HS không được tự làm, không rèn kỹ năng. Nguồn video chủ yếu lấy từ YouTube hoặc video thí nghiệm cấp 3 có sẵn. HS tự thiết kế còn tìm được cả video nước ngoài, làm trên Canva, nhiều khi tốt hơn cả GV. Video nên tắt tiếng/chú thích để HS tự quan sát và rút ra kết luận.
20/05/2026 | Những thí nghiệm nào HS được làm trực tiếp trên lớp? | Phỏng vấn GV Hóa |  | Medium |  | Closed | Chỉ các thí nghiệm cơ bản/dễ và an toàn: phân biệt ancol đơn/đa chức với Cu(OH)2, đốt sắt trong oxy, Na tác dụng nước, phản ứng tráng gương của glucozơ... GV gọi HS lên làm, GV quan sát và hướng dẫn. Thí nghiệm độc (clo, phenol+brom...) chỉ có ở ĐH vì cần tủ hốt – GV từng hít phải clo khi làm, ảnh hưởng sức khỏe.
20/05/2026 | Quy trình soạn bài hiện tại và bước nào tốn thời gian nhất? | Phỏng vấn GV Hóa |  | High |  | Closed | Quy trình: soạn giáo án → tạo câu hỏi/phiếu học tập/đề thi → tạo slide (PowerPoint) → dạy. Bước tốn thời gian nhất là thiết kế & sắp xếp slide, chèn video vào slide, và viết công thức hóa học (chỉ số trên/dưới, công thức hữu cơ gần như không làm được nếu không có công cụ hóa). Mỗi lớp (A vs D) phải soạn slide khác nhau → tốn thêm thời gian. GV chưa dùng web mô phỏng, chủ yếu PowerPoint.
20/05/2026 | GV đánh giá các chức năng của web (tạo giáo án, slide, mô phỏng 3D, thí nghiệm ảo) thế nào? | Phỏng vấn GV Hóa |  | High |  | Closed | GV đánh giá rất tích cực. Các chức năng demo: (1) mô hình 3D nguyên tử/phân tử (VD hemoglobin), bảng tuần hoàn 3D – giúp trực quan hóa kiến thức khó hình dung (cấu tạo nguyên tử, lai hóa sp/sp2/sp3, phức chất); (2) cân bằng phương trình tự động (kể cả PT khó như FeSO4+KMnO4+H2SO4); (3) thí nghiệm ảo (cho kim loại + axit, tính phản ứng thật); (4) thư viện video thí nghiệm theo SGK; (5) tự tạo slide từ giáo án (không cần PowerPoint/Canva). GV mong nhất: mô phỏng nguyên tử/phân tử và cơ chế phản ứng.
20/05/2026 | Quy trình thí nghiệm ảo (thêm chất, cân đong, quan sát) có thiếu gì so với thực tế? | Phỏng vấn GV Hóa |  | High |  | Closed | Góp ý của GV: (1) Lượng chất phải hợp lý theo SGK – demo cho 20g nhôm + 20ml axit là phi thực tế; thực tế chỉ dùng 1 lá/mảnh nhôm mỏng, 2ml axit. (2) Cần phân biệt bột nhôm vs lá nhôm (trình bày theo g hoặc ml). (3) Quy trình chuẩn cần có các bước & dụng cụ: kẹp gỗ kẹp ống nghiệm, công tơ hút lấy axit từ lọ, lọ đựng hóa chất, ống đong; bước 1 / bước 2 rõ ràng (thả kim loại trước hay đổ axit trước). (4) Hướng dẫn thao tác thường lấy từ SGK; nhưng nhiều bài (VD clo, oxy) SGK không có hướng dẫn, GV phải tự điều chế/chuẩn bị. Thí nghiệm biểu diễn quan sát hiện tượng không cần cân đong; thí nghiệm định lượng (VD trộn bột S + bột Fe) phải đúng tỉ lệ mới thành công.
20/05/2026 | Chức năng tạo slide/giáo án của web có giúp GV tiết kiệm thời gian không? | Phỏng vấn GV Hóa |  | High |  | Closed | Có, tiết kiệm nhiều thời gian. Web sinh slide từ giáo án (không cần PowerPoint/Canva), tự chèn hình ảnh/mô hình nguyên tử, viết được công thức hóa. GV ra lệnh bằng gõ hoặc nói đều được (VD: tạo giáo án 20 slide, phân bổ kiến thức cơ bản cho lớp D hoặc nâng cao cho lớp A; tạo 10 câu trắc nghiệm/đúng sai để củng cố). Có thể chỉnh sửa giáo án trước khi sinh slide. Lưu ý: GV phải kiểm tra lại độ chính xác kiến thức ở bước cuối; slide tải về dùng offline được (trường mạng yếu).
20/05/2026 | Chức năng kiểm tra nhanh & chấm điểm có hữu dụng không? Lo ngại về gian lận? | Phỏng vấn GV Hóa |  | High |  | Closed | Rất hữu dụng – GV muốn kiểm tra nhanh ~5 câu ngay sau một đơn vị kiến thức và có điểm luôn, vừa củng cố vừa nắm được HS hiểu bao nhiêu %. Vấn đề: HS KHÔNG được dùng thiết bị thông minh trong lớp (sợ tra đáp án, không trung thực) – điện thoại cất vào hòm. Giải pháp của nhóm: HS làm bài trên GIẤY (in từ web, có mã), GV dùng app điện thoại quét để chấm → ra điểm + câu đúng/sai ngay. Tham chiếu: các cô đang mua phần mềm chấm bài ~200k; web nên cung cấp mẫu phiếu + chấm miễn phí. Lưu ý lớp 11/12 vẫn có phần tự luận.
20/05/2026 | Kiến thức/chương nào HS thấy khó nhất, cần mô phỏng trực quan? | Phỏng vấn GV Hóa |  | High |  | Closed | Khó nhất là phần trừu tượng, không nhìn thấy: cấu tạo nguyên tử (electron, proton, nơtron) – chương đầu lớp 10; cấu tạo phân tử/hợp chất hữu cơ; lai hóa sp/sp2/sp3 (CH4, C2H4, C2H2); cơ chế phản ứng (VD cơ chế gốc); phức chất (tứ diện, bát diện – mới đưa vào cuối lớp 12). Đây là những phần mô hình 3D/mô phỏng có giá trị nhất vì giúp cả GV lẫn HS dễ hiểu hơn.
20/05/2026 | Bộ Cánh Diều có sách riêng cho GV không? Bối cảnh chung & kỳ vọng. | Phỏng vấn GV Hóa |  | Low |  | Closed | Không còn sách GV riêng như xưa, chỉ có SGK (dùng để tham khảo trình tự & dạng câu hỏi). Chương trình mới chủ yếu dạy phương pháp học/tự tìm hiểu, HS tự đọc được. Bối cảnh: không phải HS nào cũng yêu/chọn hóa (lớp D không học hóa); mục tiêu làm HS yêu thích & hiểu bản chất, học để có kiến thức sinh tồn chứ không chỉ để thi. GV đánh giá cao dự án, muốn là người đầu tiên trải nghiệm khi web hoàn thiện. Đề xuất: nguồn video nên có cơ chế duyệt/phối hợp trường cấp 3 quay bổ sung khi SGK có PT mới chưa có trên YouTube.
Open
Note on D2: ====== ID#AAAB9lCdUng KienNT (2026-06-07 07:38:03) Individual or Group who is responsible to handle this issue

## TimeLogs
Date | Reporter | Task | # hours | Activity | Type | Product | Work Product | Status | Updated | Notes
2026-05-05 | Đăng | Init idea - project | 4.5 | Analyzing | Newly-Create | Software Package | https://github.com/konan-1947/edua-system/commit/12409d879e10c51dc9701a90783fa71966e5775d | Submitted
2026-05-05 | Hiệp | Init setup mobile EDUA | 6 | Analyzing | Newly-Create | Software Package | https://github.com/konan-1947/edua-system/commit/d1f0337fa143a297d2e49dbd1b12df70f49ba510 | Submitted
2026-05-06 | Đăng | Create slide content | 8 | Analyzing | Newly-Create | Software Package | https://github.com/konan-1947/edua-system/commit/d849103b4cdd214c806313b01c247c5ec16a0b7e | Submitted
2026-05-08 | Đăng | Add lesson choices for AI | 7 | Analyzing | Newly-Create | Software Package | https://github.com/konan-1947/edua-system/commit/82e99ddf3c5704ef17f9643a6a182355123bd258 | Submitted
2026-05-08 | Bách | Research Chemistry domain knowledge | 8.5 | Analyzing | Newly-Create | Software Package | https://github.com/EduA-system/docs | Submitted
2026-05-07 | Nhạ | Generate lesson outline | 7 | Analyzing | Newly-Create | Software Package | https://github.com/konan-1947/edua-system/commit/44693a227c1af966d45be6931910e2d90918625b | Submitted
2026-05-08 | Hiệp | Seperate slides to avoid duplicates | 4.5 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/e2aed28b4843960aa11a1675f278957b661f2b3a | Submitted
2026-05-08 | Minh | Generate slide images with openai | 9 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/fb636f23131d02d1fed8801acd805bb3e4f40c0c | Submitted
2026-05-10 | Đăng | Change the workflow: create the lesson plan first, then create the slides. | 7 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/108b4b99d6db7e4df895cd71b718054cf87a18d3 | Submitted
2026-05-10 | Nhạ | Create slide deck | 9 | Analyzing | Newly-Create | Software Package | https://github.com/konan-1947/edua-system/commit/f9932dc77ddfe74fc3dbe4aab9035c1af57de122 | Submitted
2026-05-10 | Hiệp | Research and study mobile libraries (flutter). | 10 | Analyzing | Newly-Create | Software Package | Chưa up | Submitted
2026-05-11 | Minh | Save slide deck | 2 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/431b019a49cc30e8d487cbed7df8bd7e15f219c9 | Submitted
2026-05-11 | Bách | Analyze basic Chemistry concepts (atoms, molecules, substances) | 9 | Analyzing | Newly-Create | Software Package | https://github.com/EduA-system/docs | Submitted
2026-05-13 | Đăng | WebSocket slide generation process | 8 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/374dee4a47d798190717fe0d95ce5a5203d3f1e3 | Submitted
2026-05-15 | Đăng | Create editor slide | 9 | Analyzing | Newly-Create | Software Package | https://github.com/konan-1947/edua-system/commit/431b019a49cc30e8d487cbed7df8bd7e15f219c9 | Submitted
2026-05-17 | Bách | Make a survey of chemistry teacher | 6 | Analyzing | Newly-Create | Software Package | https://docs.google.com/forms/d/1JGRQEMi5mEM2KG2a1DmZHIjOl5pmx_I_CcIXeUeS6Hg/edit?usp=forms_home&ouid=109243146533675872684&ths=true | Submitted
2026-05-18 | Đăng | Creating a chemical experiment (Laboratory) | 10.5 | Analyzing | Newly-Create | Software Package | https://github.com/konan-1947/edua-system/commit/d7ced9844c6eb9e69937fb175eb666b93f8ae1eb | Submitted
2026-05-19 | Nhạ | Improve the quality of test tube graphics. | 7 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/b76a7246e9c8e9f8a8a4f3cef51daa378370d1cb | Submitted
2026-05-19 | Minh | Improve image - graphics, room chemistry | 7 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/215c367940a8a58d82020a984bb089e7bdc91369 | Submitted
2026-05-19 | Bách | Set up a meeting offline and Q&A with teacher in Le Quy Don High School | 6 | Analyzing | Newly-Create | Software Package | https://docs.google.com/spreadsheets/d/1eWQVKwx3ogzFHEsnMvQAi6v4PHzXzAPX/edit?gid=1727167639#gid=1727167639 | Submitted
2026-05-17 | Bách | Complete report 1 | 9 | Designing | Newly-Create | Report1 (Intro) | https://docs.google.com/document/d/1Kir0_RYBf2Xa74rZrSBHWYMrWqBB-f6g/edit | Submitted
2026-05-19 | Bách | Complete report 2 | 9 | Designing | Newly-Create | Report2 (Plan) | https://docs.google.com/spreadsheets/d/1eWQVKwx3ogzFHEsnMvQAi6v4PHzXzAPX/edit?gid=164383916#gid=164383916 | Submitted
2026-05-13 | Hiệp | Learn more about commonly used libraries in mobile-EDUA | 7 | Analyzing | Updating | Software Package | Chưa up | Rejected
2026-05-20 | Đăng | 2D Chemistry Simulation Test | 9 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/b3ba4104508975e4d3fd2f1cb9f88d2ec75b862f | Submitted
2026-05-23 | Minh | Improve the 2D page interface. | 9 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/43eb83ae579dcd7428129d32d0181d594e0bb123 | Submitted
2026-05-25 | Nhạ | Revise the background interface of the chemistry experiment simulator. | 8.5 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/700af655585854d1a554b736ef19d01c4147eeb5 | Submitted
2026-05-23 | Đăng | Modify the system prompt for the Chemistry simulation. | 8 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/34e0a09fb7b4d3d2e436abac279025790978f3d5 | Submitted
2026-05-21 | Nhạ | Add hompage landingpage | 7.5 | Analyzing | Newly-Create | Software Package | https://github.com/konan-1947/edua-system/commit/8ddbd01d71ecc4f73143ec464b97a7e31378cb55 | Submitted
2026-05-15 | Hiệp | Learn mobile interface design. | 7 | Analyzing | Newly-Create | Software Package | Chưa up | Submitted
2026-05-22 | Nhạ | Improve the landing page interface. | 8 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/2a137142b42efa09bfecfbf9773ba86381333a78 | Submitted
2026-05-25 | Đăng | Simulation test (Physical simulation) | 9 | Analyzing | Newly-Create | Software Package | https://github.com/konan-1947/edua-system/commit/aab8a4e4ff8d62a943327864b2d74e08ac77118a | Rejected |  | Redesign the physics simulation architecture to replace hardcoded individual simulations with a more scalable approach
2026-05-25 | HIệp | Research design of physical entity catalogs. | 8 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/ebf9a27939c14b50bef310f7eadf0223889e542a | Submitted
2026-05-27 | Đăng | Designing Phydyc library for 3D physics simulation. | 12.5 | Analyzing | Newly-Create | Software Package | https://github.com/konan-1947/edua-system/commit/00dd0d8a0a07698e95289fb7f5ab3a3487e23cad | Submitted
2026-05-28 | Đăng | AI generates physics simulations through conversation. | 10.5 | Analyzing | Newly-Create | Software Package | https://github.com/konan-1947/edua-system/commit/f48c3824ee44b39879c5746848e307422d9e2c5e | Submitted
2026-05-19 | HIệp | Scan and grade multiple-choice test papers. | 10.5 | Analyzing | Newly-Create | Software Package | Chưa up | Rejected |  | Failed due to lack of understanding of the technology
2026-05-29 | Đăng | New Physics Stream: AI doesn't generate code, only selects templateId + params | 11.5 | Analyzing | Newly-Create | Software Package | https://github.com/konan-1947/edua-system/commit/745d1ddd9bb6c071bdbbd52681a6551e121cfbac | Approved
2026-05-21 | Hiệp | Rework Scan for multiple-choice test paper (detect paper). | 10.5 | Analyzing | Updating | Software Package | https://github.com/EduA-system/mobile/commits/main/ | Submitted
2026-05-25 | Entire team | Cancel the plan to make a mobile app | 2 | Analyzing | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/5fe5e50eb508dcfb7aff46e3aca87d0e2ed1f8cf | Submitted |  | Remove mobile application development from the project scope
2026-05-25 | Minh | Add hydraulic-lift 3D template library for AI model3d pipeline | 8 | Analyzing | Updating | Software Package | Chưa thấy | Submitted
2026-05-26 | Hiệp | Add others model 3D template library for AI model3d pipeline | 7.5 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/c19edbba652477979d1dfee18c0250eedf6312ff | Submitted
2026-05-26 | Nhạ | Add interactive periodic table UI (element cards, detail panel, category filter, legend) | 9 | Analyzing | Newly-Create | Software Package | https://github.com/konan-1947/edua-system/commit/00589769b5d0692bb3137bb10f2ce5727d198aa1 | Submitted
2026-05-25 | Bách | Math research | 8 | Analyzing | Newly-Create | Software Package | https://github.com/EduA-system/docs | Rejected
25/5/2026 | Hiệp | Refactor model3d to 2-call AI flow (selector + generator) | 8 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/cb3f13409e295bac47a9e76252a56a47412603dc | Submitted
2026-05-27 | Bách | Math simulation research | 6 | Analyzing | Newly-Create | Software Package | https://github.com/EduA-system/docs | Submitted
2026-05-27 | Đăng | Research feasibility of converting AI-generated HTML slides to structured editor format | 8 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/e80556ebde76eb86731145c486384fe839b2b30c | Submitted
2026-05-28 | Minh | Add a new 3D modeling process to the workflow. | 6 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/136fafc0dfef5f32ec5eb6819f229c4fd5f88599 | Submitted
2026-05-28 | Hiệp | Read and understand 5512, review the current lesson plan flow, and think about integration directions. | 7 | Analyzing | Newly-Create | Software Package | https://github.com/konan-1947/edua-system/blob/main/research/soan-giao-an-theo-5512.md | Submitted
2026-05-28 | Bách | Read and write a report describing the background and functions of the system. | 6 | Analyzing | Newly-Create | Report1 (Intro) | https://docs.google.com/document/d/1Kir0_RYBf2Xa74rZrSBHWYMrWqBB-f6g/edit | Submitted |  | Review materials and prepare a report describing the system background and functionalities
2026-05-28 | Bách | Read and write a report describing the background and functions of the system. | 6 | Analyzing | Newly-Create | Report1 (Intro) |  | Submitted |  | Review and refine the context diagram by incorporating additional context, business model elements, and relevant use cases
2026-05-30 | Minh | Attempting to improve the 3D model of the physical machine. | 7 | Analyzing | Updating | Software Package | Chưa thấy | Rejected
2026-05-31 | Minh | Convert the physics simulation model to 2D. | 7 | Analyzing | Updating | Software Package | Chưa thấy | Rejected
2026-05-28 | Nhạ | Research on the accuracy of physics experiments based on formulas. | 8 | Analyzing | Updating | Software Package | Chưa thấy | Submitted
2026-05-30 | Minh | Integrate 5512 into lesson plan creation. | 8 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/efb7afb1d6a658398c0169377e8618e63a08325f | Submitted
2026-05-30 | Hiệp | Clone Gemini CLI, install DeepSeek key + generate physics simulation. | 9 | Analyzing | Newly-Create | Software/System |  | Rejected
2026-06-01 | Đăng | Clone Gemini CLI, install DeepSeek key + generate physics simulation. | 7.5 | Analyzing | Newly-Create | Software Package |  | Rejected
2026-06-02 | HIệp | Integrate outline flow ⇒ n slide | 7 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/dbf40fbb2926e0864664fc61a7322864e43a3057 | Submitted
2026-06-01 | Bách | Do some more new surveys on mathematics. | 6 | Analyzing | Updating | Software Package | https://drive.google.com/file/d/17XqA1BNBzLlgxIL0ynRRswJ4zBgFX5bt/view?usp=drive_link | Rejected |  | Design and conduct additional surveys to gather insights on Mathematics teaching challenges
2026-06-01 | Nhạ | Read and experiment on the structure of matter with r3f | 7 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a0 | Submitted |  | Research and experiment with modeling atomic and molecular structures using React Three Fiber (R3F)
2026-06-02 | Nhạ | Read the slide editor - complete the rest. | 9 | Analyzing | Updating | Software Package | https://github.com/konan-1947/edua-system/commit/efb7afb1d6a658398c0169377e8618e63a08325f | Submitted
2026-06-03 | Minh | Read how to simulate the hub - perform an experiment (draw the process using a diagram). | 7 | Analyzing | Newly-Create | Software Package | Ảnh trong group EDUA | Submitted
2026-06-01 | Bách | Complete feature tree | 6 | Designing | Newly-Create | Report1 (Intro) | https://docs.google.com/document/d/1Kir0_RYBf2Xa74rZrSBHWYMrWqBB-f6g/edit | Submitted
2026-06-03 | Bách | Do the survey again. | 4.5 | Analyzing | Updating | Report1 (Intro) | https://docs.google.com/forms/d/e/1FAIpQLSfJsCAuVCBBXitBnD6VIr9ZaUbSOWHBGM2e1JSNEiRzviEK-Q/viewform?usp=sharing&ouid=106581367712518385710 | Submitted
2026-06-03 | Bách | Summary survey | 4.5 | Analyzing | Newly-Create | Report1 (Intro) | https://docs.google.com/forms/d/e/1FAIpQLSciqD2pHsRqckAVJ_b7hPoO1xfec5lQuuHXzNGhriEZ3zInFA/viewform | Submitted
2026-06-05 | Minh | Create a form for listing chemical materials. | 6 | Analyzing | Newly-Create | Software Package | Ảnh trong group EDUA | Submitted
2026-06-05 | Bách | usecase diagram | 6 | Analyzing | Updating | Report3 (SRS) | https://docs.google.com/document/d/1k-zmEbSi-0-JRTPFZCBuMamoZ8J7jgmq/edit#heading=h.1ejj1i9iz7vs | Submitted
2026-06-10 | Bách | Edited and completed report 1 | 7 | Analyzing | Updating | Report1 (Intro) | https://docs.google.com/document/d/1Kir0_RYBf2Xa74rZrSBHWYMrWqBB-f6g/edit | Submitted |  | 1.4 System Functionalities 1.4.1 Screens Flow 1.4.2 Screen Authorization 1.4.3 Non-UI Functions
2026-06-18 | Minh | Learn and apply test criteria. | 6 | Analyzing | Newly-Create | Report3 (SRS) | https://docs.google.com/document/d/14Ktx6PHkqeLEp2QGDqyBJ0l3eXwZ6dA2iOYWr4Nz-CY/edit?usp=sharing | Submitted
2026-06-04 | Đăng | Design a use case for a teacher | 6 | Analyzing | Updating | Report3 (SRS) | https://docs.google.com/document/d/1k-zmEbSi-0-JRTPFZCBuMamoZ8J7jgmq/edit?rtpof=true&tab=t.0 | Submitted
2026-06-04 | Minh | Create a mock-up for the system. | 7 | Analyzing | Updating | Report3 (SRS) | https://docs.google.com/document/d/1k-zmEbSi-0-JRTPFZCBuMamoZ8J7jgmq/edit?rtpof=true&tab=t.0 | Approved
2026-06-04 | Nhạ | Design a mock-up for the system. | 7 | Analyzing | Updating | Report3 (SRS) | https://docs.google.com/document/d/1k-zmEbSi-0-JRTPFZCBuMamoZ8J7jgmq/edit?rtpof=true&tab=t.0 | Approved
2026-06-06 | Đăng | Design of components under SDS-Report 4 | 8 | Analyzing | Newly-Create | Report4 (SDS) | https://docs.google.com/document/d/1etvw2cpsLKOy7XJ1aLdv1KXNxRytwh_e/edit?rtpof=true&tab=t.0 | Submitted
2026-06-07 | Hiệp | Detail design and High-Level Design are part of SDS. | 9 | Analyzing | Updating | Report4 (SDS) | https://docs.google.com/document/d/1etvw2cpsLKOy7XJ1aLdv1KXNxRytwh_e/edit?rtpof=true&tab=t.0 | Approved
2026-06-06 | Bách | Continued working on improving Report 3 | 8 | Analyzing | Updating | Report3 (SRS) | https://docs.google.com/document/d/1k-zmEbSi-0-JRTPFZCBuMamoZ8J7jgmq/edit?rtpof=true&tab=t.0 | Submitted
2026-06-08 | Bách | Edited and completed the final versions of Report 1 and Report 2 | 9 | Analyzing | Updating | Report2 (Plan) | https://docs.google.com/document/d/164qbyJSsoI8972fnl6Iiil80-IGnrPJX/edit?rtpof=true&tab=t.0 | Submitted
2026-06-13 | Đăng | Project- setup/initialization | 6 | Coding | Newly-Create | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a0 | Approved
2026-06-13 | Đăng, Hiệp | AI generate lesson plan from SGK data (Be) | 11.5 | Coding | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a1 | Approved
2026-06-13 | Nhạ, Minh | AI generate lesson plan from SGK data (Fe) | 11.5 | Coding | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a2 | Approved
2026-06-15 | Hiệp | Create lesson plan from uploaded file (BE) | 12.5 | Coding | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a3 | Approved
2026-06-15 | Nhạ | Create lesson plan from uploaded file (FE) | 12.5 | Coding | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a4 | Approved
2026-06-15 | Đăng | Edit & approve lesson plan(BE) | 10.5 | Coding | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a5 | Approved
2026-06-17 | Hiệp, Đăng | Create slide outline (BE) | 10.5 | Coding | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a6 | Approved
2026-06-17 | Nhạ, Minh | Make screen create -edit outline | 11.5 | Coding | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a7 | Approved
2026-06-18 | Đăng | Edit slide outline(BE) | 9 | Coding | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a8 | Approved
2026-06-19 | Đăng | AI Generate Slide from Confirmed Outline(BE) | 12.5 | Coding | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a9 | Approved
2026-06-18 | Hiệp | Edit slide (BE) | 10.5 | Coding | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a10 | Approved
2026-06-18 | Nhạ, Minh | Make screen create -edit slide | 12.5 | Coding | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a11 | Approved
2026-06-18 | Hiệp | Export / download lesson (HTML) for offline | 9 | Coding | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a12 | Approved
2026-06-19 | Đăng | Create test (3 frames: 15p / 45p / mid-term) | 12.5 | Coding | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a13 | Approved
2026-06-19 | Minh | Make exam screen | 10.5 | Coding | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a14 | Approved
2026-06-19 | Hiệp | Export exam to printable file | 8 | Coding | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a15 | Approved
2026-06-19 | Nhạ, Minh | Make hub screen | 10.5 | Coding | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a16 | Approved
2026-06-20 | Hiệp, Đăng | Save & organize lessons / slides / custom simulations | 9 | Coding | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a17 | Approved
2026-06-20 | Đăng | Export Lesson Plan (PDF/Word) BE | 8 | Coding | Reviewing | Software Package | https://github.com/konan-1947/edua-system/commit/7e7a17b3fa1d81d764d1e3e5f6b8ecc89ef306a18 | Approved
2026-06-18 | Bách | Completed Report 3 | 9 | Analyzing | Reviewing | Report3 (SRS) | https://docs.google.com/document/d/1k-zmEbSi-0-JRTPFZCBuMamoZ8J7jgmq/edit?rtpof=true&tab=t.0 | Submitted
2026-06-20 | Bách | Researching Report 5: Test Planning | 7 | Analyzing | Reviewing | Report5 (Test) | https://docs.google.com/document/d/1EWSn5mXpg_J0LQMMPgu3UuZm8EcHBpSi/edit?rtpof=true | Approved

## Defects
Project Defects
Date | Defect Description | Activity | Product | Product Details | Assigner | Assignee | Status | Updated | Notes
2026-06-13 | Project setup faced minor challenges with the folder structure and database configuration. | Review | Software Package |  | Đăng | Đăng | Closed | 2026-06-13 | The problem was resolved that same day.
2026-06-14 | The challenge in choosing an AI provider. | Review | Software Package |  | All team | All team | Assigned | 2026-06-15 | Choosing an AI provider can be challenging due to the need to balance price and quality.
2026-06-17 | The lesson plan editor did not correctly synchronize slide content after editing, causing outdated information to be displayed. | Review | Software Package |  | Đăng | Nhạ | Closed | 2026-06-17
2026-06-18 | AI lesson plan generation API returned incorrect response when processing uploaded SGK files due to request validation issues. | Review | Software Package |  | Đăng | Hiệp | Closed | 2026-06-18 | Validation logic was corrected and the API returned the expected response.
2026-06-23 | An error occurred while using the command to run the project in the README file on GitHub. | Review | Software Package |  | Hiệp | Đăng | Pending | 2026-06-23
Note on E2: ====== ID#AAAB9lCdUno None (2026-06-07 07:38:03) Name of screen, function or the document section

## Issues
Project Issues
Date | Issue | Type | Priority | Created | Owner | Due Date | Status | Notes
2026-05-26 | Cancel the plan to make a mobile app due to scope mismatch | Type 2 | Medium | Entire team | Entire team | 2026-05-26 | Closed
| Inefficient allocation of human resources. | Type 2 | High | Entire team | Entire team |  | Closed
2026-06-12 | Running out of AI tools | Type 1 | High | Entire team | Entire team |  | In Progress
2026-05-24 | Simulation test (Physical simulation) | Type 2 | High | Đăng | Đăng | 2026-05-25 | Closed | Converting Physics instruments into 3D models is highly complex and not scalable for large volumes. It is difficult to define a common framework and unified logic for modeling different types of instruments.
2026-05-19 | Scan and grade multiple-choice test papers. | Type 2 | Medium | HIệp | HIệp | 2026-05-20 | Closed | Due to time constraints, the team is unable to develop a mobile application within the planned schedule.
2026-05-25 | Math research | Type 2 | Medium | Bách | Bách | 2026-05-25 | Closed | Mathematics involves numerous algebraic formulas that are not suitable for 2D/3D visualization, while spatial geometry lacks effective solutions to support teaching. Additionally, long-established teaching habits make it difficult to change user behavior.
2026-05-30 | Attempting to improve the 3D model of the physical machine. | Type 2 | Medium | Minh | Minh | 2026-05-30 | Closed | AI struggles with pathing components and workflow integration
2026-05-31 | Convert the physics simulation model to 2D. | Type 2 | Medium | Minh | Minh | 2026-05-31 | Closed | AI is unable to process physical workflows
2026-06-01 | Clone Gemini CLI, install DeepSeek key + generate physics simulation. | Type 2 | High | Đăng Hiệp | Đăng Hiệp | 2026-06-02 | Closed | Converting Physics instruments into 3D models is highly complex and not scalable for large volumes. It is difficult to define a common framework and unified logic for modeling different types of instruments.
2026-06-01 | Do some more new surveys on mathematics. | Type 2 | Medium | Bách | Bách | 2026-06-01 | Closed